## Change Charter
NIATx Change Project Charter
Change Project Title:
1. The Change Team: Who do we need to achieve this goal?
List your team members below. (Try to include between 4 and 7 members)
Does our team include the people needed to address key quality issues. Does our team include diverse experience? | Identify the team members above who will serve as the Change Leader and the Data Coordinator
Who is the Change Leader?
Who is the Executive Sponsor?
2. The Big Aim: What needs improving? What outcome do we seek?
What is the problem or issue your are facing?
What is the improved outcome you would like to see?
Combine the above two responses into one sentence to summarize your Big Aim:
3. The Focused Aim = Big Aim + Process + Customer
To correct the problem identified in the "Big Aim" above, what process will you focus on improving?
Who is the customer of the process you've identified?
4. The Aim Statement & Data Plan: How will we measure the change?
Indicator: How will we measure our progress?
Baseline: What is the measure of the indicator before we start the change?
Goal: How much progress do we hope to achieve? (stretch goal of % or # improvement)
Date: how long will we run the change project?
Write your Aim Statement as a sentence: (Improve I from B to G by D)
5. The Walk-Through: How does it feel to be the participant/partner?
What process did you walk through & why?
Who completed the walk-through?
Were there steps in the process that were not needed?
Which steps needed improvement?
How did you feel as you completed the process?
6. The Flowchart: What does the process look like?
Draw a flowchart map of the walk through process | See flowchart tab
Are there steps/boxes that can be improved?
Are there transitions/arrows that can be improved?
Note possible fixes for flaws in steps & transitions
7. The Nominal Group Technique (NGT): What change strategies might work?
Conduct an NGT with your team to answer a version of this question: What change can we make that will result in a measurable improvement toward the focused aim above?
8. The Change Strategy Selection Process: Which change strategy will we test first?
Describe the change strategy that was selected to test first from your during the NGT exercise.
9. The PDSA Rapid Cycle Test: What are the results of your change strategy test?
Enter PDSA Cycle details below using the information from the PDSA tabs in the spreadsheet. Check the appropriate box for the "ACT Phase" you did for each PDSA Cycle: Adopt, Adapt, or Abandon.
PDSA #1: Name of change tested | Brief description here | FALSE | Adopt | FALSE | Adapt | FALSE | Abandon
PDSA #2: Name of change tested | Brief description here | FALSE | Adopt | FALSE | Adapt | FALSE | Abandon
PDSA #3: Name of change tested | Brief description here | FALSE | Adopt | FALSE | Adapt | FALSE | Abandon
10. Complete the Change Project: Sustainability & Sharing Your Story
A) Sustainability: Answer the questions below to create a sustainability plan for your change project.
1) Choose a Sustain Leader: List the name of the person responsible for making sure the new procedure is followed correctly; monitoring the data; and engaging leadership if the data slips to unacceptable levels.
2) Standardize the Change: Describe the new "changed process" and the staff position responsible for monitoring the data in the future. Remember to update any procedure manuals in your organization to include the changed process.
3) Collect and Review Data: Describe the method you will use for collecting and analyzing data relevant to your process change.
4) Determine What Is and Is Not Acceptable: State how much fluctuation in the data from the achieved improvement goal, is acceptable and determine at what point action will be taken. (e.g., "If we see this specific data number for this specific amount of time, we will take action.")
5) Set the Change Date: What is the official start date for implementing the changed process? Remember to make sure all details and instructions for the new procedure are clearly communicated to the appropriate staff prior to the date.
B) Sharing Your Story: Provide the slide information below to share results and lessons learned from your change project using the 5x5 Presentation Model. (e.g., Five PowerPoint slides presented in five minutes)
Additional Notes: Type here
SLIDE 1 - Aim
Change Project Title
Change Team Members (add photo if you have it)
Aim Statement (see Step 4)
SLIDE 2 - Change
The process you focused on improving
The changes you tested
Where and with whom you tested the changes
SLIDE 3 - Results
Display the data results from your PDSA cycles
If you created a line chart of the data results, include it on this slide
SLIDE 4 - Next Steps
Describe what you learned
Describe what you plan to do next with the knowledge you gained from the change project results.
SLIDE 5 - Impact
What was the impact on the customers or clients you serve?
What was the impact on staff?
What was the impact on the organization? (e.g., financial, efficencies, etc.)

## Walk-through
Walk-through
Enter the notes from your walk-through on this page for reference. (See EXAMPLE Walk-through tab)
Download the Walk-through tool here: | https://niatx.wisc.edu/the-5-tools/
Walk-through Recording Template
Date
Team Members
Location / Service Area
Process
What worked well?
What could be improved?
Improvement Ideas Identified:
Additional Comments & Observations

## Flowchart
Flowchart
Use the symbols below to create a flowchart or insert a photo from your whiteboard flowchart exercise on this page. (See EXAMPLE Flowchart tab)
Download the Flowchart tool here: | https://niatx.wisc.edu/the-5-tools/
Start
Process step
End
Desion point in the process - which is a yes/no question
?
YES
NO

## NGT
Nominal Group Technique (NGT) |  | Enter the change strategies, or a photo, from your NGT exercise on this page for reference. (See EXAMPLE NGT tab)
|  | Download the NGT tool here: | https://niatx.wisc.edu/the-5-tools/
No. | Change Strategy Idea
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## PDSA 1
Download the PDSA tool here: | https://niatx.wisc.edu/the-5-tools/
PDSA Cycle
PDSA Cycle #1:
What is the change to be tested?
Location
Testing Timeframe | Start Date: Month/Day/Year End Date: Month/Day/Year
PLAN: What are the logistics we need to address prior to doing the change? Who will be responsible for the various tasks? Are there any new documents or forms we need to create?
DO: Did we carry out the change test according to our plan? If not, document what was different.
STUDY: What were the data results? Team Discussion Questions: Was the change successful and did the data move in a positive direction? Why or why not? Did we carry out the test according to our plan? What did staff say about the change – was it easy or difficult to implement? Did the change make the process better for our customers or clients and/or staff? Would staff be able to sustain the change if it became a standard procedure? Could the results of this change be improved if we adapted the change in some way and re-tested it?
ACT: (choose one) | ___Abandon ___Adapt ___Adopt
Why did you choose your "Act" response listed above?
If you chose to Abandon, which strategy idea from your NGT list will you pursue for a next PDSA?
If you chose to Adapt, how will you adjust the strategy for a 2nd PDSA?
If you chose to Adopt, how will you sustain and spread the strategy?

## PDSA 2
Download the PDSA tool here: | https://niatx.wisc.edu/the-5-tools/
PDSA Cycle
PDSA Cycle #2:
What is the change to be tested?
Location
Testing Timeframe | Start Date: Month/Day/Year End Date: Month/Day/Year
PLAN: What are the logistics we need to address prior to doing the change? Who will be responsible for the various tasks? Are there any new documents or forms we need to create?
DO: Did we carry out the change test according to our plan? If not, document what was different.
STUDY: What were the data results? Team Discussion Questions: Was the change successful and did the data move in a positive direction? Why or why not? Did we carry out the test according to our plan? What did staff say about the change – was it easy or difficult to implement? Did the change make the process better for our customers or clients and/or staff? Would staff be able to sustain the change if it became a standard procedure? Could the results of this change be improved if we adapted the change in some way and re-tested it?
ACT: (choose one) | ___Abandon ___Adapt ___Adopt
Why did you choose your "Act" response listed above?
If you chose to Abandon, which strategy idea from your NGT list will you pursue for a next PDSA?
If you chose to Adapt, how will you adjust the strategy for a 2nd PDSA?
If you chose to Adopt, how will you sustain and spread the strategy?

## PDSA 3
Download the PDSA tool here: | https://niatx.wisc.edu/the-5-tools/
PDSA Cycle
PDSA Cycle #3:
What is the change to be tested?
Location
Testing Timeframe | Start Date: Month/Day/Year End Date: Month/Day/Year
PLAN: What are the logistics we need to address prior to doing the change? Who will be responsible for the various tasks? Are there any new documents or forms we need to create?
DO: Did we carry out the change test according to our plan? If not, document what was different.
STUDY: What were the data results? Team Discussion Questions: Was the change successful and did the data move in a positive direction? Why or why not? Did we carry out the test according to our plan? What did staff say about the change – was it easy or difficult to implement? Did the change make the process better for our customers or clients and/or staff? Would staff be able to sustain the change if it became a standard procedure? Could the results of this change be improved if we adapted the change in some way and re-tested it?
ACT: (choose one) | ___Abandon ___Adapt ___Adopt
Why did you choose your "Act" response listed above?
If you chose to Abandon, which strategy idea from your NGT list will you pursue for a next PDSA?
If you chose to Adapt, how will you adjust the strategy for a 2nd PDSA?
If you chose to Adopt, how will you sustain and spread the strategy?

## EXAMPLE Change Charter
NIATx Change Project Charter
Change Project Title: | Calling All Parents & Caregivers
1. The Change Team: Who do we need to achieve this goal?
List your team members below. (Try to include between 4 and 7 members)
1 Sally Williams - program coordinator | 5 Bob Brooks (Parent/Caregiver)
2 Janice Campbell - Riverton high school secretary
3 Jim Olson - data coordinator
4 Katie Jones (Parent/Caregiver)
Does our team include the people needed to address key quality issues Does our team include diverse experience? | Identify the team members above who will serve as the Change Leader and the Data Coordinator
Who is the Change Leader? | Donna Smith
Who is the Executive Sponsor? | Mark Thomas
2. The Big Aim: What needs improving? What outcome do we seek?
What is the problem or issue you are facing? | Not enough people are showing up to our Family Engagement program meetings.
What is the improved outcome you would like to see? | Increased meeting attendance
Combine the above two responses into one sentence to summarize your "Big Aim." | Average meeting attendance is too low for our Family Engagement program and we need to increase attendance rates.
3. The Focused Aim = Big Aim + Process + Customer
To correct the problem identified in the "Big Aim" above, what process will you focus on improving? | Our parent and caregiver communication process
Who is the customer of the process you've identified? | Parents and caregivers of school-aged children
4. The Aim Statement & Data Plan: How will we measure the change?
Indicator: How will we measure our progress? | Average attendance rates to Family Engagement program meetings.
Baseline: What is the measure of the indicator before we start the change? | Average of 23 attendees per meeting
Goal: How much progress do we hope to achieve? (stretch goal of % or # improvement) | Average of 37 attendees per meeting (61% improvement)
Date: how long will we run the change project? | 12-weeks Start Date: April 1 End Date: June 30
What is your Aim Statement? (Improve I from B to G by D) | Increase attendance rates to Family Engagement program meetings from 23 attendees to 37 attendees per meeting by June 30.
5. The Walk-Through: How does it feel to be the participant/partner?
What process did you walk through & why? | Pre-meeting communication process with parents/caregivers. We have a hunch they are forgetting about the meetings due to their busy schedules.
Who completed the walk-through? | On April 4, the entire change team did a "talk-through" of the pre-meeting communication process and how we notify parents/caregivers of upcoming program meetings.
Were there steps in the process that were not needed? | No
Which steps needed improvement? | The team agreed we need to how we inform and remind parents/caregivers of upcoming meetings, without sending too many emails.
How did you feel as you completed the process? | Felt like it could be easy to forget about a scheduled meeting and maybe the time of the meeting is not optimal for parents/caregivers schedules.
6. The Flowchart: What does the process look like?
Draw a flowchart map of the walk through process | See flowchart tab
Are there steps/boxes that can be improved? | Add steps to send reminder emails to parents/caregivers.
Are there transitions/arrows that can be improved? | None identified
Note possible fixes for flaws in steps & transitions | Send reminder emails closer to the date of the meeting.
7. The Nominal Group Technique (NGT): What change strategies might work?
Conduct an NGT with your team to answer a version of this question: What change can we make that will result in a measurable improvement toward the focused aim above?
8. The Change Strategy Selection Process: Which change strategy will you test first?
Describe the change strategy that was selected to test first from your during the NGT exercise.
1) Send a reminder email to parents/caregivers 3-days prior to a program meeting. 2) Send a reminder email to parents/caregivers the day-of the program meeting. 3) Change the start time of the program meeting to a later time slot.
9. The PDSA Rapid Cycle Test: What are the results of your change strategy test?
Enter PDSA Cycle details below using the information from the PDSA tabs in the spreadsheet. Check the appropriate box for the "ACT Phase" you did for each PDSA Cycle: Adopt, Adapt, or Abandon.
PDSA #1: 3-day Reminder Email | Send a reminder email to parents/caregivers 3-days prior to a program meeting. | FALSE | Adopt | TRUE | Adapt | FALSE | Abandon
PDSA #2: Same-day Reminder Email | Send a reminder email to parents/caregivers on the day of a program meeting. | TRUE | Adopt | FALSE | Adapt | FALSE | Abandon
PDSA #3: Later Meeting Start Time | Move the start time of the program meetings from 6pm to 7pm. | TRUE | Adopt | FALSE | Adapt | FALSE | Abandon
10. Complete the Change Project: Sustainability & Sharing Your Story
A) Sustainability: Answer the questions below to create a sustainability plan for your change project.
1) Choose a Sustain Leader: List the name of the person responsible for making sure the new procedure is followed correctly; monitoring the data; and engaging leadership if the data slips to unacceptable levels. | Sally Williams (Family Engagement Program Coordinator)
2) Standardize the Change: Describe the new "changed process" and the staff position responsible for monitoring the data in the future. Remember to update any procedure manuals in your organization to include the changed process. | 1) Three days prior to a program meeting, the Family Engagement Program Coordinator will send a reminder email to all parents/caregivers on the program list serve. The coordinator will monitor email and reply to any questions from parents/caregivers. 2) The Program Coordinator will send a final email reminder the day of each program meeting. This reminder will be sent no later than 10am the day of the meeting.
3) Collect and Review Data: Describe the method you will use for collecting and analyzing data relevant to your process change. | 1) At each Family Engagement program meeting and sign-in sheet will be completed by attendees. 2) The Program Coordinator will enter total attendee numbers into the Family Engagement Program master data tracking spreadsheet in the office. 3) Each month the Program Coordinator will provide an "attendance report" at the monthly "All-staff meeting."
4) Determine What Is and Is Not Acceptable: State how much fluctuation in the data from the achieved improvement goal, is acceptable and determine at what point action will be taken. (e.g., "If we see this specific data number for this specific amount of time, we will take action.") | The sustainment goal is to meet or exceed an average of 37 attendees at Family Engagement program meetings. If the average attendance drops below 37 for three consecutive months, the Program Coordinator will notify leadership and a corrective action plan will be developed.
5) Set the Change Date: What is the official start date for implementing the changed process? Remember to make sure all details and instructions for the new procedure are clearly communicated to the appropriate staff prior to the date. | August 1
B) Sharing Your Story: Provide the slide information below to share results and lessons learned from your change project using the 5x5 Presentation Model. (e.g., Five PowerPoint slides presented in five minutes)
Title: Calling All Parents & Caregivers Change Team Members: Donna Smith, Sally Williams, Janice Campbell, Jim Olson, Katie Smith, Bob Brooks Aim Statement: Increase attendance rates to Family Engagement program meetings from 23 to 37 attendees per meeting by June 30.
Process Focus: The parent/caregiver communicaiton process Location: Tested changes with the Riverton High School Family Engagement program Changes Tested: 1) Send a reminder email to parents/caregivers 3-days prior to a program meeting. 2) Send a reminder email to parents/caregivers the day-of the program meeting. 3) Change the start time of the program meeting to a later time slot, from 6pm to 7pm.
The reminder emails 3-days prior to the program meeting did not improve attendance. Sending a reminder email the day-of the meeting improved attendance by 26%. Changing the meeting start time from 6pm to 7pm made the greatest improvement with a 44% increase in attendance. Together, both changes (day-of reminders and a 7pm meeting start time), increased meeting attendance rates by 61% compared to our pre-change, baseline data. We are now averaging 39 attendees per meeting which has exceeded our change project aim of 37 attendees.
Lessons Learned: We discovered from the "talk-through" of our communication process that many variables were present as to why parents/caregivers were not showing up for meetings. The change team conducted phone interviews with parents and caregivers and this provided the need insight into their busy world. We discovered that parents and caregivers are even busier than we thought and need last minute reminders. They also told us they need time to get home from work, thus a later meeting start time is better for them. Quite a few parents and caregivers at the program meetings thanked us for sending the day-of reminder emails. We were also surprised how much of a difference the 7pm meeting start time made in improving attendance rates. Next Steps: 1) Adopt day-of reminder emails and the 7pm meeting start time and re-test it with two additional high schools. 2) If the second test is successful, implement the new process across the school district. 3) Share our findings with other outreach programs.
Customers: More parents were able to attend and engage in our program sessions. Staff: The change team was encourage by how a few simple changes resulted in a significant improvement to our parent attendance. Organization: We are currently meeting our Family Engagement outreach goals. By reaching and engaging more parents and caregivers, our organization realizes a greater return on investment for each program dollar spent.
Additional Notes: Type here
SLIDE 1 - Aim
Change Project Title
Change Team Members (add photo if you have it)
Aim Statement (see Step 4)
SLIDE 2 - Change
The process you focused on improving
The changes you tested
Where and with whom you tested the changes
SLIDE 3 - Results
Display the data results from your PDSA cycles
If you created a line chart of the data results, include it on this slide
SLIDE 4 - Next Steps
Describe what you learned
Describe what you plan to do next with the knowledge you gained from the change project results.
SLIDE 5 - Impact
What was the impact on the customers or clients you serve?
What was the impact on staff?
What was the impact on the organization? (e.g., financial, efficencies, etc.)

## EXAMPLE Walk-through
Walk-through
Enter the notes from your walk-through on this page for reference.
Download the Walk-through tool here: | https://niatx.wisc.edu/the-5-tools/
Walk-through Recording Template
Date | 2025-03-01
Team Members | Donna Smith, Jim Olson, Sally Williams
Location / Service Area | Riverton High School
Process | Parent & Caregiver Communication Process (Family Engagement Program)
What worked well? | The email production and distribution process was standardized and delivered timely and consistently to parents and caregivers who were signed up for the Family Engagement Program. The reminder emails were clear and concise.
What could be improved? | We discovered that we need to better understand how parents and caregivers want to receive communications and meeting reminders from us.
Improvement Ideas Identified: | We decided that to really understand the communication needs of parents/caregivers, we need to conduct some phone interviews with parents/caregivers and ask them what type of communications they prefer and are there any other strategies that would make it easier for them to attend program meetings?
Additional Comments & Observations | We discovered there and many variables that contribute to whether or not busy parents/caregivers will open the email reminders.

## EXAMPLE Flowchart
Flowchart
Complete your flowchart or insert a photo of it on this page for reference.
Download the Flowchart tool here: | https://niatx.wisc.edu/the-5-tools/
Flowchart Process Name: Parent/Caregiver Communication Process for the Family Engagement Program
Schedule program meeting
Send email to notify parents & caregivers 3-weeks prior to the meeting
Send reminder email to parents & caregivers 1-week prior to meeting
Conduct the onsite program meeting
Did a parent or caregiver send back any questions from either email?
Send email response to parent or caregiver
YES
NO
Start
End

## EXAMPLE NGT
Nominal Group Technique (NGT)
Enter the change strategies (or a photo) from your NGT exercise on this page for reference. |  | Download the NGT tool here: | https://niatx.wisc.edu/the-5-tools/
No. | Change Strategy Idea
1 | Have meeting attendees register online and system sends reminder
2 | Later meeting time
3 | Use an email marketing service
4 | Handout a flyer at each meeting
5 | Leave a meeting reminder card with school secretary
6 | Announce meeting over school P.A. and ask students to reminder parents of meeting
7 | Reminder email the day of the meeting
8 | Text reminder
9 | Have teachers announce meeting to students to tell parents/caregivers
10 | Create "Parent Leads" to help remind other parents
11 | Reminder email 3-days before meeting
12 | Have snacks at every meeting
13 | Send a meeting reminder card home with kids to give to parents/caregivers
14 | Phone call reminders
15 | Mail a monthly calendar to parents/caregivers with meeting dates and times
16 | Place meeting poster outside near student pickup/drop location
17 | Postcard reminder sent in mail
18 | Display meeting poster in school office
19 | Allow parents/caregivers to sign up for "text alerts" of coming meetings
20 | Place reminder cards on meeting charis with date & time of next meeting
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## EXAMPLE PDSA 1
PDSA Cycle
PDSA Cycle #1: Reminder email 3-days prior
What is the change to be tested? | Send a reminder email to parents/caregivers 3-days prior to the scheduled meeting to see if it increases attendance rates.
Location | Riverton High School - Family Engagement Program
Testing Timeframe | 3-week test period. Start Date: April 14 End Date: May 2
PLAN: What are the logistics we need to address prior to doing the change? Who will be responsible for the various tasks? Are there any new documents or forms we need to create? | 3-days prior to Family Engagement meetings, the program coordinator will send an email to the list serve of parents/caregivers who signed up for the program, reminding them of the upcoming meeting. Sally will create a standardized reminder email template. Program meeting facilitators will enter meeting attendance numbers into the main attendance log spreadsheet. Jim will serve as data coordinator. He will create a line chart and enter meeting attendance numbers every Friday for the 3-week testing period. We will be able to gather data results for three meetings over the testing period.
DO: Did we carry out the change test according to our plan? If not, document what was different. | Reminder emails were sent on the following dates: April 14, 21, 28. The program meetings took place on April 17, 24 and May 1, all at 6pm. Notes: Out of the 78 email addresses in the parent/caregiver list serve, three were returned “undeliverable.” All three reminder emails were sent around 2pm in the afternoon.
STUDY: What were the data results? Team Discussion Questions: Was the change successful and did the data move in a positive direction? Why or why not? Did we carry out the test according to our plan? What did staff say about the change – was it easy or difficult to implement? Did the change make the process better for our customers or clients and/or staff? Would staff be able to sustain the change if it became a standard procedure? Could the results of this change be improved if we adapted the change in some way and re-tested it? | Attendance Data Results: Apr. 17 meeting = 22 Apr. 24 meeting = 24 May 1 meeting = 23 Conclusion: Average meeting attendance pre-change = 23 attendees and post-change = 23 attendees. This change did not produce any improvement in the attendance rate.
ACT: (choose one) | ___Abandon X Adapt ___ Adopt
Why did you choose your "Act" response listed above? | We chose to adapt the change and do another PDSA cycle test. Instead of sending a 3-day reminder email, we would test sending a reminder the "day of" the meeting.
If you chose to Abandon, which strategy idea from your NGT list will you pursue for a next PDSA?
If you chose to Adapt, how will you adjust the strategy for a 2nd PDSA? | We think sending a reminder email the day-of the meeting may yield better results.
If you chose to Adopt, how will you sustain and spread the strategy?

## EXAMPLE PDSA 2
PDSA Cycle
PDSA Cycle #2: Reminder email, day-of
What is the change to be tested? | Send a reminder email to parents/caregivers the day-of the scheduled meeting to see if it increases attendance rates.
Location | Riverton High School - Family Engagement Program
Testing Timeframe | 3-week test period. Start Date: May 5 End Date: May 23
PLAN: What are the logistics we need to address prior to doing the change? Who will be responsible for the various tasks? Are there any new documents or forms we need to create? | The day-of a Family Engagement meeting at 9am, the program coordinator will send an email to the list serve of parents/caregivers who signed up for the program, reminding them of the meeting. Sally will create a standardized reminder email template. Program meeting facilitators will enter meeting attendance numbers into the main attendance log spreadsheet. Jim will serve as data coordinator and create a change project line chart to display data results. He will enter meeting attendance numbers into the line chart every Friday for the 3-week testing period.
DO: Did we carry out the change test according to our plan? If not, document what was different. | Day-of reminder emails were sent on the following dates: May 8, 15, 22. The program meetings took place on the same days, all at 6pm. Notes: Out of the 78 email addresses in the parent/caregiver list serve, three were returned “undeliverable.” All three reminder emails were sent around 9:30am.
STUDY: What were the data results? Team Discussion Questions: Was the change successful and did the data move in a positive direction? Why or why not? Did we carry out the test according to our plan? What did staff say about the change – was it easy or difficult to implement? Did the change make the process better for our customers or clients and/or staff? Would staff be able to sustain the change if it became a standard procedure? Could the results of this change be improved if we adapted the change in some way and re-tested it? | Attendance Data Results: May 8 meeting = 29 May 15 meeting = 28 May 22 meeting = 30 Conclusion: Average meeting attendance pre-change = 23 attendees and post-change = 29 attendees. This change produced a 26% improvement in the attendance rate.
ACT: (choose one) | ___Abandon ___ Adapt X Adopt
Why did you choose your "Act" response listed above? | We chose to adopt the change because it produced a 26% increase in meeting attendance and it is easy for staff to sustain and it costs very little to implement.
If you chose to Abandon, which strategy idea from your NGT list will you pursue for a next PDSA?
If you chose to Adapt, how will you adjust the strategy for another PDSA? | Since we did not reach our project aim of 37 meeting attendees, we will run another PDSA cycle testing a new change strategy.
If you chose to Adopt, how will you sustain and spread the strategy? | The program coordinator will make "day-of meeting reminder emais" part of their standard parent/caregiver communication process.

## EXAMPLE PDSA 3
PDSA Cycle
PDSA Cycle #3: 7pm meeting start time
What is the change to be tested? | Move Family Engagement program meeting start times from 6:00pm to 7:00pm, to see if it increases attendance rates.
Location | Riverton High School - Family Engagement Program
Testing Timeframe | 3-week test period. Start Date: May 26 End Date: June 13
PLAN: What are the logistics we need to address prior to doing the change? Who will be responsible for the various tasks? Are there any new documents or forms we need to create? | The meeting facilitators for the Family Engagement program have been notified of the time change idea and are in agreement to moving the start time of all meetings from 6pm to 7pm. The program coordinator will send an email to parents/caregivers announcing the new 7:00pm start time and continue to send “day-of meeting email reminders.”
DO: Did we carry out the change test according to our plan? If not, document what was different. | May 26: An email was sent by the program coordinator to the list serve of 75 parents announcing the new program meeting time of 7:00pm. Day-of meeting email reminders were sent to parents/caregivers on the following dates: May 29, June 5, 12. ame-day reminder email was sent at 9:30am by the program coordinator to a list of 75 parents reminding them of the meeting scheduled for Nov. 18 @ 7:00pm. NOTE: Three "undeliverable" email address were removed from the list serve making the total 75 email addresses.
STUDY: What were the data results? Team Discussion Questions: Was the change successful and did the data move in a positive direction? Why or why not? Did we carry out the test according to our plan? What did staff say about the change – was it easy or difficult to implement? Did the change make the process better for our customers or clients and/or staff? Would staff be able to sustain the change if it became a standard procedure? Could the results of this change be improved if we adapted the change in some way and re-tested it? | Attendance Data Results: May 29 meeting = 40 June 5 meeting = 38 June 12 meeting = 39 Conclusion: Average meeting attendance pre-change = 27 attendees and post-change = 39 attendees. This change produced a 44% improvement in the attendance rate.
ACT: (choose one) | ___Abandon ___ Adapt X Adopt
Why did you choose your "Act" response listed above? | We chose to adopt the change because it produced a 44% increase in meeting attendance and it is easy for staff to sustain and there is zero cost to implement it.
If you chose to Abandon, which strategy idea from your NGT list will you pursue for a next PDSA?
If you chose to Adapt, how will you adjust the strategy for another PDSA?
If you chose to Adopt, how will you sustain and spread the strategy? | All Family Engagement program staff will make the 7pm start time a standard practice.